## Sheet1
Date | Report |  | Data/Modeling |  | Visualization |  | Presentation |  | Homework
| Item | Who | Item | Who | Item | Who | Item | Who
2020-03-19 | Format report template | Miggs | Review data sets + brainstorm models | Everyone
2020-03-20
2020-03-21 | Complete intro + problem definition + survey sections | Miggs | Compile list of possible models by 12PM EST Team call discussing datasets + models (1-3) + evaluation | Everyone Everyone | Brainstorm possible visualizations based on selected models + datasets | Lisa/Cathy
2020-03-22 | QC intro/prob def/survey sections | Everyone | Data cleansing | Marc | At least 1 visualization wireframe | Lisa/Cathy
2020-03-23 | Proposed method section | Miggs | Data integration Model skeletons (in python?) | Ricardo/MK Ricardo/MK
2020-03-24 | QC intro/prob def/survey sections | Everyone | Testbed creation (list of questions) Details of experiments Run some models for preliminary results | Marc/Cathy Marc/Cathy Ricardo/MK | All visualization wireframe(s) | Lisa/Cathy
2020-03-25 | Draft experiments and conclusions sections | Miggs
2020-03-26 | Review/finalize/submit
2020-03-27 | Progress Report Due
2020-03-28
2020-03-29
2020-03-30
2020-03-31
2020-04-01
2020-04-02
2020-04-03
2020-04-04 | [8 empty] | HW 4 due
2020-04-05
2020-04-06
2020-04-07
2020-04-08
2020-04-09
2020-04-10
2020-04-11
2020-04-12 | [6 empty] | Finish poster | Lisa
2020-04-13
2020-04-14
2020-04-15 | [6 empty] | Finish recording | Everyone
2020-04-16
2020-04-17 | Final Report Due |  | Final Report Due |  | Final Report Due |  | Poster Presentation Due